## WBS
TaskId | Team | Epic | Task | TaskType | SubTask | SubTaskType | Status | Priority | PlannedPersonDay | PlannedPersonDayPerAssignee | PlannedStartDate | PlannedEndDate | PersonDay | StartDate | EndDate | Assignee | Description | Version | BlockedBy | Tags[Tag1] | PV | EV | AC | AccumulatedPersonDay | AccumulatedStartDate | AccumulatedEndDate
TASK-1 |  | MyEpic | [6 empty] | 0 | [11 empty] | 0 | 0 | 0 | 0
TASK-2 |  | MyEpic | MyTask | Task |  |  |  |  | 0 | [11 empty] | 0 | 0 | 0 | 0
TASK-3 |  | MyEpic | MyTask | Defect | MySubTask | SubTask |  |  | 1 | 2 | 2025-04-01 | 2025-04-04 |  |  |  | ichiro.yamada |  |  |  |  | 1 | 0 | 0 | 2 | 2025-04-01 | 2025-04-04
TASK-4 |  | MyEpic | MyTask | Defect | MySubTask2 | SubTask |  |  | 2 | 4 | 2025-04-04 | 2025-04-10 |  |  |  | ichiro.yamada |  |  |  |  | 2 | 0 | 0 | 6 | 2025-04-04 | 2025-04-10
TASK-5 |  | MyEpic | MyTask | Defect | MySubTask3 | SubTask |  |  | 3 | 6 | 2025-04-10 | 2025-04-18 |  |  |  | ichiro.yamada |  |  |  |  | 3 | 0 | 0 | 12 | 2025-04-10 | 2025-04-18
TASK-6 |  | MyEpic | MyTask2 | Task |  |  |  |  | 0 | [11 empty] | 0 | 0 | 0 | 0
TASK-7 |  | MyEpic | MyTask2 | Task | MySubTask2 | SubTask |  |  | 2.5 | 2.5 | 2025-04-02 | 2025-04-07 |  |  |  | jiro.suzuki |  |  |  |  | 2.5 | 0 | 0 | 2.5 | 2025-04-02 | 2025-04-07
TASK-8 |  | MyEpic | MyTask2 | Task | MySubTask3 | SubTask |  |  | 5 | 5 | 2025-04-07 | 2025-04-14 |  |  |  | jiro.suzuki |  |  |  |  | 5 | 0 | 0 | 7.5 | 2025-04-07 | 2025-04-14
TASK-9 |  | MyEpic | MyTask2 | Task | MySubTask3 | SubTask |  |  | 6 | [11 empty] | 6 | 0 | 0 | 0
Formulas:
AccumulatedStartDate = IF(WBS[[#This Row],[Assignee]]="", "", WORKDAY(XLOOKUP(WBS[[#This Row],[Assignee]], Assignee[Assignee], Assignee[StartDate], "-", 0),WBS[[#This Row],[AccumulatedPersonDay]]-WBS[[#This Row],[PlannedPersonDayPerAssignee]], Holiday[Holiday]))
AccumulatedEndDate = IF(WBS[[#This Row],[Assignee]]="", "", WORKDAY(XLOOKUP(WBS[[#This Row],[Assignee]], Assignee[Assignee], Assignee[StartDate], "-", 0),WBS[[#This Row],[AccumulatedPersonDay]], Holiday[Holiday]))
PlannedStartDate = WBS[[#This Row],[AccumulatedStartDate]]
PlannedEndDate = WBS[[#This Row],[AccumulatedEndDate]]

## master
■variables
OvertimeRatePerDay(Default1)
1
■master
Status | TaskType | SubTaskType | Priority | Assignee | StartDate | ProjectRatio | Team | Version | Holiday
ToDo | Deliverable | Review | Highest | - |  |  | Team1 | v0.01 | 2025-04-03
Doing | Defect | FeedBack | High | ichiro.yamada | 2025-04-01 | 0.5
UnderReview | Issue | SubTask | Medium | jiro.suzuki | 2025-04-02 | 1
Done | ToDo |  | Low
| Task |  | Lowest